## Budget Detail
Anticipated Cost Report — 11320 Biscayne Blvd
Account | Original Budget | Budget Change | Revised Budget | Contract | Unapproved | Non-Contract Inv | Contract Inv | Total Invoiced | Committed | Anticipated Cost | Final Cost | ETC | Over/Under Budget
011100 - Land Deposit - Non-Refundable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
011300 - Contract Purchase Price | 13500000 | 0 | 13500000 | 0 | 0 | 13500000 | 0 | 13500000 | 13500000 | 0 | 13500000 | 0 | 0
011500 - Brokerage Commissions | 250000 | -250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
011600 - Tenant Buy-Outs | 1091000 | 83638.3 | 1174638.3 | 0 | 0 | 1174638.3 | 0 | 1174638.3 | 1174638.3 | 0 | 1174638.3 | 0 | 0
011800 - Seller Reimbursable Costs | 1316523 | -300000.24 | 1016522.76 | 0 | 0 | 1016522.76 | 0 | 1016522.76 | 1016522.76 | 0 | 1016522.76 | 0 | 0
021100 - Owner's insurance Policy | 70000 | -36675 | 33325 | 0 | 0 | 33325 | 0 | 33325 | 33325 | 0 | 33325 | 0 | 0
021200 - Mortgage Ins Policy - Base | 100000 | -100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
021600 - Recording Fees | 5000 | -2566.5 | 2433.5 | 0 | 0 | 2433.5 | 0 | 2433.5 | 2433.5 | 0 | 2433.5 | 0 | 0
021900 - Ancillary Closing Costs | 30000 | -27500 | 2500 | 0 | 0 | 2500 | 0 | 2500 | 2500 | 0 | 2500 | 0 | 0
031100 - Legal - Acquisition | 35274 | 208999.5 | 244273.5 | 0 | 0 | 244273.5 | 0 | 244273.5 | 244273.5 | 0 | 244273.5 | 0 | 0
031200 - Legal - Construction | 17692 | 36159.76 | 53851.76 | 0 | 791.35 | 60481.76 | 0 | 61273.11 | 60481.76 | 20000 | 80481.76 | -7421.35 | -26630
031220 - Legal - Zoning, Land Use, Etc | 461024 | 241480.33 | 702504.33 | 0 | 7694.25 | 707851.78 | 0 | 715546.03 | 707851.78 | 0 | 707851.78 | -13041.7 | -5347.45
031260 - Legal - Environmental | 267598 | -50000 | 217598 | 0 | 14500 | 191779 | 0 | 206279 | 191779 | 0 | 191779 | 11319 | 25819
032300 - Legal - Entity | 4163 | 5994.53 | 10157.53 | 0 | 0 | 10157.53 | 0 | 10157.53 | 10157.53 | 0 | 10157.53 | 0 | 0
033200 - Legal - Commercial Lease | 250 | 28678 | 28928 | 0 | 0 | 29925.5 | 0 | 29925.5 | 29925.5 | 0 | 29925.5 | -997.5 | -997.5
034100 - Legal - Contracts | 0 | 277.95 | 277.95 | 0 | 0 | 11210.65 | 0 | 11210.65 | 11210.65 | 0 | 11210.65 | -10932.7 | -10932.7
041100 - Concept Design & Site Planning | 32575 | 68378.48 | 100953.48 | 113680 | 0 | 0 | 100953.48 | 100953.48 | 100953.48 | 0 | 113680 | 0 | -12726.52
041200 - Architect | 1911241 | 366621.52 | 2277862.52 | 4072264 | 275301 | 1982.65 | 2048651.71 | 2325935.36 | 2050634.36 | 0 | 4074246.65 | -48072.84 | -1796384.13
041500 - Interior Designer | 300000 | -300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
042100 - Survey | 8200 | 64628.75 | 72828.75 | 148350 | 5000 | 19132.5 | 98346.25 | 122478.75 | 117478.75 | 0 | 167482.5 | -49650 | -94653.75
042200 - Zoning/Political Consultants | 180000 | -168524 | 11476 | 0 | 0 | 11476 | 0 | 11476 | 11476 | 0 | 11476 | 0 | 0
042300 - Civil Engineer | 320930 | 41220.21 | 362150.21 | 744050 | 0 | 1949.92 | 433275.29 | 435225.21 | 435225.21 | 0 | 745999.92 | -73075 | -383849.71
042400 - Geotech Engineer | 100000 | 0 | 100000 | 90625 | 0 | 3000 | 90625 | 93625 | 93625 | 0 | 93625 | 6375 | 6375
042500 - Landscape Architecture | 115000 | -115000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
042800 - Other Consulting | 19050 | 143755 | 162805 | 178900 | 1188.65 | 11000 | 169755 | 181943.65 | 180755 | 200 | 190100 | -19138.65 | -27295
042810 - Traffic Engineer Contract | 15000 | -15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
042830 - Phase 1 & Phase 2 | 113089 | 88990.29 | 202079.29 | 272900 | 5265 | 0 | 245744.29 | 251009.29 | 245744.29 | 0 | 272900 | -48930 | -70820.71
042860 - Flora & Fauna Consultant | 8080 | 0 | 8080 | 8000 | 0 | 80 | 8000 | 8080 | 8080 | 0 | 8080 | 0 | 0
042880 - Permit Expeditor | 60000 | 0 | 60000 | 45675 | 0 | 0 | 990 | 990 | 990 | 0 | 45675 | 59010 | 14325
042890 - Low Voltage Designer | 20000 | -20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
045300 - Material Testing | 0 | 0 | 0 | 209115 | 0 | 0 | 0 | 0 | 0 | 0 | 209115 | 0 | -209115
045500 - Inspections | 0 | 2875 | 2875 | 217169 | 0 | 0 | 4375 | 4375 | 4375 | 0 | 217169 | -1500 | -214294
045510 - ADA/FHA Inspector | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000
045520 - Green Consultant | 10000 | 0 | 10000 | 71410 | 6500 | 0 | 20000 | 26500 | 20000 | 0 | 71410 | -16500 | -61410
045540 - Power Company Consultant/Expeditor | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000
045550 - Envelope Consultant | 13500 | 5636 | 19136 | 126560 | 1440 | 0 | 29216 | 30656 | 29216 | 0 | 126560 | -11520 | -107424
045570 - Fire Service Engineer | 35000 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000
045580 - Scheduling Consultant | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000
051100 - Local Site Plan Fee | 45000 | 0 | 45000 | 0 | 0 | 34478.36 | 0 | 34478.36 | 34478.36 | 0 | 34478.36 | 10521.64 | 10521.64
051200 - County Site Plan Fee | 0 | 38424.46 | 38424.46 | 0 | 0 | 38424.46 | 0 | 38424.46 | 38424.46 | 0 | 38424.46 | 0 | 0
051300 - Minor Admin. Review Fees | 0 | 16670.63 | 16670.63 | 0 | 0 | 18665.7 | 0 | 18665.7 | 18665.7 | 0 | 18665.7 | -1995.07 | -1995.07
052100 - Utility Consumption Fee | 0 | 15128.71 | 15128.71 | 0 | 2668.56 | 18035.3 | 0 | 20703.86 | 18035.3 | 0 | 18035.3 | -5575.15 | -2906.59
053200 - Building Permits | 45000 | 229638.27 | 274638.27 | 0 | 0 | 293775.29 | 0 | 293775.29 | 293775.29 | 0 | 293775.29 | -19137.02 | -19137.02
058200 - Payment & Performance Bond | 0 | 40995 | 40995 | 0 | 0 | 40995 | 0 | 40995 | 40995 | 0 | 40995 | 0 | 0
061200 - Taxes Payable During Construct | 326368 | 0 | 326368 | 0 | 0 | 310331.29 | 0 | 310331.29 | 310331.29 | 0 | 310331.29 | 16036.71 | 16036.71
062200 - Owner Liability Policy | 25000 | 1891.47 | 26891.47 | 0 | 0 | 26891.47 | 0 | 26891.47 | 26891.47 | 0 | 26891.47 | 0 | 0
062300 - Env Remediation Policy | 140000 | 0 | 140000 | 0 | 0 | 126511.35 | 0 | 126511.35 | 126511.35 | 0 | 126511.35 | 13488.65 | 13488.65
063100 - Travel | 0 | 15921.75 | 15921.75 | 0 | 0 | 18293.47 | 0 | 18293.47 | 18293.47 | 0 | 18293.47 | -2371.72 | -2371.72
063200 - Postage & Delivery | 0 | 589.24 | 589.24 | 0 | 0 | 786.65 | 0 | 786.65 | 786.65 | 0 | 786.65 | -197.41 | -197.41
063300 - Aerial Photos | 0 | 2416.75 | 2416.75 | 0 | 0 | 3216.75 | 0 | 3216.75 | 3216.75 | 0 | 3216.75 | -800 | -800
063400 - Misc Administration | 4000 | 23812.7 | 27812.7 | 0 | 0 | 37057.54 | 0 | 37057.54 | 37057.54 | 0 | 37057.54 | -9244.84 | -9244.84
063900 - Donations | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 100000 | 0 | 100000 | -100000 | -100000
103200 - Marketing & Promotion | 35000 | 10683.69 | 45683.69 | 66500 | 0 | 9183.69 | 44000 | 53183.69 | 53183.69 | 0 | 75683.69 | -7500 | -30000
191100 - Soft Cost Contingency | 511005 | -243323.22 | 267681.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267681.78 | 267681.78
250105 - GC Preconstruction Fee | 90000 | 0 | 90000 | 323232.5 | 0 | 0 | 130380 | 130380 | 130380 | 0 | 323232.5 | -40380 | -233232.5
250180 - Interim Parking | 0 | -3190 | -3190 | 0 | 0 | -56071.43 | 0 | -56071.43 | -56071.43 | 0 | -56071.43 | 52881.43 | 52881.43
250181 - Site Security | 0 | 5690 | 5690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5690 | 5690
250200 - Site Contractor | 0 | 4210 | 4210 | 0 | 0 | 4210 | 0 | 4210 | 4210 | 0 | 4210 | 0 | 0
250210 - Demolition | 730000 | -311352.13 | 418647.87 | 449538.27 | 0 | 0.1 | 418647.77 | 418647.87 | 418647.87 | 0 | 449538.37 | 0 | -30890.5
250250 - Relocate Existing Utilities | 0 | 156434.8 | 156434.8 | 0 | 0 | 156434.8 | 0 | 156434.8 | 156434.8 | 0 | 156434.8 | 0 | 0
250290 - Landscaping | 0 | 0 | 0 | 11940 | 0 | 0 | 11940 | 11940 | 11940 | 500 | 12440 | -11940 | -12440
250295 - Offsite Improvements | 0 | 0 | 0 | 0 | 0 | 99790 | 0 | 99790 | 99790 | 0 | 99790 | -99790 | -99790
251040 - Signage | 0 | 3304.76 | 3304.76 | 0 | 0 | 3304.76 | 0 | 3304.76 | 3304.76 | 0 | 3304.76 | 0 | 0
251300 - Special Construction | 0 | 2994.43 | 2994.43 | 0 | 0 | 2994.43 | 0 | 2994.43 | 2994.43 | 0 | 2994.43 | 0 | 0
291100 - Hard Cost Contingency | 41000 | -13009.19 | 27990.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27990.81 | 27990.81
399998 - Discontinued Development Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0